Work Plan

| SKILL SHORTAGE (SK-SH) e.learning in cultural diversity @LIS call (31-OCT-2002) |
| --- |
| Stage in life of project | Outputs: By the end of this stage we will have achieved / produced | Activities leading to this output | Activity to be started by this date and completed by this date | Partners / Persons involved | Time input - e.Working Time |
| 1 Early Stage : ( WP1) April-2003(July 2003 Relevance & Management - Level of complete organizational definition SK-SH project and sub-projects - “S1” All members “Sharing knowledge and net-learning services.” -a) e.brain-work networking agreement - Brainstorming of creative proposal on net-learning for facilitating EU-LA “alliance” -Survey of best practices networked organisation for overcoming “shill shortage” for knowledge -economy development in relation thematic priority of an extended EU-LA of Knowledge economy development in synergy with IS national policies and with e.Europe general strategy (see: LISBON2000, EU. Commission meeting) . b)- Project Co-ordination - To ensure the execution of the project in conformity with the Commission contract and the Consortium Agreement. Steering Commitee ceck list to coordinate the activities of each member of the consortium - To organize full communications and lines of responsibility between the partners To negotiate any necessary changes to these agreements during the project S2- Tech. Service for e. publishing and sharing net-learning tools service. Net-Meeting of S2 membership | FIRST INTERNATIONAL CONGRESS on “SKILL SHORTAGE” @LIS Program JUNE 2003. FIRENZE ITALY SK-SH “EX ANTE EVALUATION “ a) Conclusive “e. agreement” of SK-SH Consortium Organization Election of the Consultant committees (Scientific, Technological, Monitoring, Sustainability) New models of e.learning for knowledge management : preliminary report of the “state of the art”. b) 1: Mid term implementation report and final report 2 Three Managements reports and Annuals Reports to the Commission 3: Updated progress reports for the partnership 4: The production of a dynamically generated Portal and web-sites for the management of the project and for communications between the partners and other interested and involved groups/bodies. „Virtual Library“ organization. e.Working organization of HELP desk on technical and operational problems. | a) Documentation Advanced documentation on the relevance of needs and constrains of the membership countries Advanced Information for a wide synergy with “IS” national policies in the membership countries or regions. Advanced Information for improving “Alliance” in the promotion of gender equality and man/woman equal opportunities in net-learning programming - b) -Bibliographical consultation -Survey design of specific net-learning needs in relation to the thematic priorities of the SK-SH Action Plan -Field clarification of “e.Brain work” methods in an virtual “e.space” for facilitating the understanding on the changes in traditional space-time work to the SK.SH target groups -Net--Learning Management System development verification - Synthesis and reports c) Organisation of ITC resources -Teleconferences , Audio-conferences , forums, e.mailing to develop SK-SH internal „e.brain working” hypothesis and definition . - Organization of the permanent Electronic Forum of SK-SH membership SK-SH Portal & web-sites construction and adjournment in various membership languages. | Focus on: a) 01/April /2003 01/June /2003 - b) Co-odination Month 1-month 24 | All S1 Members / 20 All S2 Members /8 | a) 10% of S1 b) 10% of S1 20 % of S2 |
| SUB-Projects//TP’s Preparatory phase WP2 IMPLEMENTATION July-2003(OCT 2003 See-SUB-Project DESCRIPTION S1 Common Activities - a)General Theme implementation of SK-SH sub- Project coherent co-ordination Setting up Co-operative programme searching cognitive resources and tools of Knowledge management for IS knowledge Economy Knowledge -Economy for the development of “IS” for SME’s accreditation Selection of pedagogical models and net-learning styles for lifelong education in working SME’s environment | "systems approach" To define the user needs and requirements -To ensure and determine that the needs of the project will be met. -To realise the differing needs of the end-user partners nations regions -To establish the appropriate information/data/images from the major end user -To explore and confirm that the strategies and technologies used are appropriate for ITC interaction Pedagogical models and e.learning styles ; KM innovation for SME’s market’s internationalization FIRST WORKSHOP in CUBA OCTOBER .2003 In Itinere Evaluation | -a) - Co-ordination of SK-SH sub-project partnership multi-functional teams : - Proposals of the Scientific Committee for – net-learning and product models innovation - Proposals of Technological Commitee for e.logistics efficiency -b) - Pedagogic organisation on the basis of e.learning case studies and best practices - SME‘s collaboration in the SK-SH e.learning on demand project preliminary reports | focus on : 01/July./2003 01/Sept/ 2003 -b) Month 1 - month 6 | Al members belonging to the Steering Committee in co-operation with the Co-ordinators of Sub-Projects /10 i.e. APPLICANT (RT) (IT) PIN/LRE (IT) KCM (CO) UTFSM (CL) REDMESO (MX) UCSF (AR) PIN/LRE (IT) FOORMATEX (ES) Al members belonging to the Steering Committee in co-operation with the Co-ordinators of Sub-Projects /10 | a) 10 % of S1 b) 05 % of S1 |
| 3) Pre-operational phase Oct-2003(Jan 2004 WP3 Methodology Evaluation -Level of experimental demonstration organization Inter-partnership contents and ITC sharing co-operation - S1” All members “Sharing knowledge and net-learning services.” -Selection of content for creating models and units for innovative multilingual courseware for distant e.learning on demand “tool-kit” productions - Planning management co-organisation between S1 & S2 S2- Tech. Service for e. publishing and sharing net-learning tools service -1) Definition of technological infrastructure and open source platforms 2) -first approach to the organization of the “virtual laboratory” VIAL for e.learning on demand courseware options and bids to the SK-SH targets groups. | 1Identification of some flexible innovative models and units for the on demand e.learning system -2) dentification of e.brain work skills for career and employment programming in relation of knowledge economy business opportunities for SME’s international markets. 3)- e-educational methods comparison and selection in relation and their characteristics for “ on demand e.learning” -4) SK-SH start up orchestration in a problem based scenario of the improvement of future IS citizenship. b) Setting-up of proposals of multilingual courseware between the universities and SME’s consultant members of the SK-SH consortium -To design the preliminary structure the Basic/Prototype -Virtual Lab „VIAL“ To set up the Pilot Server (Testing - Evaluation) - To operate/maintain/update the <Virtual Lab> VIAL prototype | a) -Analysis of the selected Methodology for e-education in a contest of cultural diversity Booklet : guidelines and methods for building up on demand e.learning projects - SK-SH Project guidelines for improving STAKEHOLDER Collaborative adhesion and agreement’s contracts- -b) VIRTUAL LIBRARY -1- Thematic priority’s content documentation -2- Content images, aspects and site map -3- Report and paper on the impact of change in the future IS knowledge economy development - 4: Portal architectural structure for the implementation programs of Sub-projects | a)+ b) focus on : 01/October /2003 01/Jan/2004 b) Month 9 - month 12 | All S1 Members / 20 - All S2 Members /8 | a) 10% of S1 20% of S2 |
| 4)– SUB-Projects//TP’s Deployment phase WP4 E-Publishing and SK-SH Portal Building Jan-2004( Apr.2004 See-SUB-Project DESCRIPTION S1 Common Activities a)- Convergence and synergies with national programs in the field of knowledge management with SME’s - | a) Opening initiatives- at Regional organization or local seminar and conferences of publicising SK-SH intermediate results to facilitate the participation of SME's for developing shared knowledge to innovate constantly e.learning on demand for Knowledge management innovation b)-To ensure the technical implementation . To provide the technical specifications. To extend and develop the basic/prototype virtual lab.;To enhance the portal with a number of advanced services that will differentiate it from the other products and development environments in the market today. Including Advanced VR features. To define the architecture of the portal..To programme the additional features Second WORKSHOP in MEXICO DATE: APR r 2004 VENUE: Cuernavaca, Morelos, México The Title of the meeting and the Organization INSTITUTION ": TITLE: "INTERNATIONAL WORKSHOP: Knowledge Management for SME's Skill Building on ECO-ECONOMY" ORGANISATION INSTITUTION: RED MESOAMERICANA DE RECURSOS BIÓTICOS In Itinere Evaluation Dissemination and diffusion of the intermediate results of Sub-project implementation. | -Definition of the contents and ipertext organization of Tool-Kits prototypes for on demand e Learning useful for the SK-SH target groups. Advertising of the second Workshop on the issue “ON DEMAND “ e. LEARNING” -Detailed report of the Fourth trimester b)- --The design and integration of communication --4: Full evaluation report of intermediate activities | a) Focus on : Jan/ /2004//APR/2004 b)- month 12 – month 18 | -All members belonging to the Steering Committee in co-operation with the Co-ordinators of Sub-Projects /10 | a) 10% of S1 |
| Deonstration phase April-2004( July 2004 WP5 Level Adding Value Mission to EU-LA “Alliance” for IS common advancement through e.learning demonstrations - a) S1” All members “Sharing knowledge and net-learning services.” a) European impact and risk analysis for different productive SME’s typologies -b) forecasting for new additional income of Modules and Units to better the Tool-kits proposals -c) Continuos Diffusion and Evaluation -S2- Tech. Service for e. publishing and sharing net-learning tools service | Launching a wide -Testing proposal of Tool-Kits for on Demand e.learning -Modules testing and Units product exprimentation and diffusion Questionaries available from the SK-SH portal and membership‘s web sites: Focus on Groups, Individuals and Assessment. 2: Reports and findings 3: Detailed revision of design (if required) of tool-kits . Regular adjust of the activities in each successive phase of the SK-SH demonstrations : -Deigning of indicators ; processing and stadistical data ; getting a regular control of partial objectives in relation to the EU-LA „alliance“ results -Production of Tool-Kits prototypes for on demand e Learning useful for the SK-SH target groups containing modules and demonstration units in multi-language ipertext format. | -Comparative analysis of content e.learning on demand modules and units taking in account regional productive SME’s districts differences in a context of Knowledge management innovation of future IS Trans national development Refinement of cultural and scientific assets of tool-kits for e.learning on demand multilingual courseware production - Intermediate report of the refinement and experimentation of physical assets of all IT systems | focus on : 01/April/2004 31/July/2004 b)- month 15 – month -24 | All S1 Members / 20 All S2 Members /8 | 10% of S1 30% of S2 |
| 6)– SUB-Projects//TP’s Deployment phase WP6 Knowledge Management in wide Cultural Dicversity July-2004( Oct. 2004 See-SUB-Project DESCRIPTION S1 Common Activities | -a)-Diffusion in various membership national Languages of previous testing results on demand e.learning : - b)Monitor of S1/S2 activities - THIRD WORKSHOP MERCOSUR URUGUAY Montevideo/Punta del Este OCTOBER - 2004 In Itinere Evaluation | 1- Self-assessment, on-line 2: Comprehensive co-organiation web sites links 3: Information brochure 4: Printed information document 5: CD-ROM | a) Focus on 01 /July/ 2004 01 /Sept. 2004 b)- - w.p. revision and new e brain work subdivision : (‘)About work plan developmental innovation arrangement (‘’) About obtained products: (‘’)Month 15-month 24 About permanent infrastructure VIAL and Sustainability and result Dissemination (‘) Month 18 - month 24 (‘’) About obtained products: (‘’)Month 15-month 24 | All members belonging to the Steering Committee in co-operation with the Co-ordinators of Sub-Projects /10 | a) 05 % of S1 b) 05% of S1 |
| 7- Permanent organization Oct-2004(Dec. 2004 WP7 Permanent network infrastructure -Level of Manteinance and infrastructure long-term organization Phase “VIAL “ organization acting as a multiplier effects of on demand e.learning potentiality and e.publishing dissemination for promoting EU-LA co-operation in IS C) S2- Tech. Service for e. publishing and sharing net-learning tools service -a) S1” All members “Sharing knowledge and net-learning services.” | a) SK-SH PORTAL and Web-Sites Links developed using advance features of e.learning open sorce software and low cost platforms and ITC – tools Ensure the VIAL permanent infrastructure works across the regions and fulfils the main objectives. To test the response to the interface design. To test via focus groups in the geographical areas. To ensure universality of the desig of SK-SH permenent infrastucture. b) SK-SH - KNOW-HOW „intellectual property issues firecast “after the end of the Eu-Grant FOUR WORKSHOP BADAJOS Spain Organization FORMATEX (ES) DECEMBER 2004 In Itinere Evaluation | -Preliminary Organisation of Final Reports for International Congress promotion , Diffusion and dissemination of the Results Testing the SK-SH Portal and Platform Organisation for synchronous e.learning activities Testing and refining the <Virtual Lab.> „VIAL“ b) International low recognition that legitimate Intellectual Property Right (IPR) issues | a) Focus on 01/Oct /2004 01 /December/2004 | All S2 Members / 10 All S1 Members / 10 | 30% of S2 05% of S1 |
| 8- Sustainability Final Phase. Dec-2004(April 2005 WP8 – Wide Action concerning Sustainability and Dissemination ) S1” All members “Sharing knowledge and net-learning services.” -Business case analysis Commercial Plan - Diffusion and dissemination of final results - Opening of the new commercial phase in a Ethic Business Strategy - First year: conclusive evaluation . | Creating “Business-Ethics” case models to allowing the SK-SH activities to continue be in place at the end of EU-Grant. Building an implementation tele-woking teams through Stakeholder Network agreement for the future sustainability of VIAL permenent Infrastructure. - Providing realistic levels of financial resources for getting a developmental sustainabble Ethic-business feedback. Seaching for local „owership“ of SK-SH project Outcomes. b) Break –even analisys in Business - Definition of Intellectual property rights issues in relation to the SK-SH –KNOW.HOW. -To evaluate strategic direction for Ethics business goals of future sustainability .-To Assess the costumer expectation,competitor pressure and quality of products in a coherent vision of e.learning market evolution -To Estimate the cost /time for product design and development. To reconsider a business plan .To develop a system of self assessment. To look at future commercialisation. To develop a comprehensive commercial portal for the SK-SH project in a business ethics developmental strategy for implement the future IS Society Knowledge Economy. . - Certification & Credits Unit Definitive proposal Opening new alliances and joint ventures implementing management processes and financial system. - Final evaluation report and global improvement proposals FINAL CONGRESS in CHILE APRIL 2005 Organization Universidad Tecnica Federico Santa MAria Collanoration: Intendencia Regional Valparaiso -Camara De la Produccion y el Comercio -Instituto Internacional Para la Innovacion Empresarial EX –POST EVALUATION | Final public Congress on the issue :(at the end of second semester): -– Conclusive Accreditation Courses proposals -About the obtained products: -Product analysis Drawing up global improvement proposals Writing of the evaluation for final report | focus on 01 /December /2004 31 /March/ 2005 | All S1 Members / 30 | 20% of S1 |